Revised 6/28/23 Appendix 3

**CAMPUS ELECTIONS COMMISSION CALENDAR**

**2024 Spring Quarter Election** (exact dates are subject to CEC meeting schedule)

Quarter Week Day Item \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Fall 3 th Ad notifying campus of need to file intent to circulate

petition and submit a proposal for the 2024 election by

Oct. 28 (Oct. 19th)

 5 f **November 3 – Intent Forms Due**

 6 t-f CEC meets to review intent forms (week of Nov. 6)

 CEC notifies GSA of any intents that include grad students

(by November 10)

6-8 CEC works with proponents to finalize petition language

which includes deciding grad/undergrad signatures, information reports to relevant campus departments (see Guidelines) and student governments with intent to receive feedback for proponents to work out any questions, concerns, etc.(Nov. 6 - Nov. 24)

 9 m-f CEC approves petition language (week of Nov. 27)

CEC sends approved petitions to ballot hopefuls by Dec. 1

Winter 1 m Petition gathering begins (Jan. 8)

 1 f **Reaffirmation proposal forms due (Jan. 12)**

5 t **Petitions due** **(Feb. 6)**

 **GSA Assembly votes to place measure on joint CEC ballot and notifies CEC (Feb. GSA meeting). If fails, proponents have 30 more days to obtain grad signatures**

 5 f Petitions verified (Feb. 9)

 6 th **Proposal Forms due (Feb. 15)**

 9 t Campaign Meeting (Week of March 4)

10 m-f Ballot language and Voter's Guide finalized (Mar.11-15)

Spring 1 th Sample ballot and Voter’s Guide pub. in Nexus (April 4)

 2 th Pro/con statements due (Apr. 11, 5:00PM)

 3 s Official start of campaigning (Apr. 14, 8pm)

 3 w, th Pro/con statements pub. in Nexus (Apr. 18)

 4 m-th Undergraduate/Graduate election (Apr. 22-25)

4 m Election begins 8:00 AM (Apr. 22)

 4 th Election ends 4:00 PM, Ballots tabulated

8:00 PM (Apr. 25)

 6 w Election results memo to Chancellor (May 8)